## Risk Register
Risk ID | Risk Item | Impact | Likelihood | Risk Score | Comments | Mitigation
Mitigation |  | Mitigation | Mitigation |  |  | Mitigation
1 | Complexity of System Interfaces - System Interface requiredments becomes complex to handle | 4 | 2 | 4.4721 | Understanding the no of interfaces with other systems and their requirements | Draft the user requirements and meet-up with the customer face-to-face to run through the URS to iorn out any gaps or misunderstandings on the system interface requirements
2 | Technical Complexity - No of technical components that the team ha limited knowledge at this time | 4 | 3 | 5 | Understanding the technical complexity of the project and being able to deliver the project | Project team to conduct and carry out necessary POC during iterration 0 to get familirize with the hardware technology
3 | User Requirements to confirm the scope - Clarity on the scope and next level user requirements | 4 | 2 | 4.4721 | Finalization of User requirements | Draft the user requirements and meet-up with the customer face-to-face to run through the URS to iorn out any gaps or misunderstandings.
4 | Expectatations on the Real time Performance of the system | 3 | 3 | 4.2426 | Expectations on the systems performance(Real time) | Well optimized code to be deployed, have reviews conducted on the code before deployment for testing to see it is well optmized. Keep the stakeholders informed of the limitations driven by the technical architecture
5 | Hardware Technology adapted by the project | 4 | 1 | 4.1231 | Project team's familiarity of the Hardware Technology to be adapted by the proposed system | Project team to conduct and carry out necessary POC during iterration 0 to get familirize with the hardware technology
6 | Finalization of Project Plan | 3 | 3 | 4.2426 | Project Plan with Mile stones and expected deliverables agreed and accepted by relevant stakeholders | Draft the project plan and meet-up with the customer face-to-face to run through the Project plan. This will help to iorn out any gaps or misunderstandings interms milestones and deliverables.
7 | Limited technical skill sets - cloud services - rich UI for real time analytic - LabView | 2 | 1 | 2.2361 |  | 1. Do some POC work to ensure the concepts is workable and doable 2. Consult some experts to get some idea
8 | Withdrawing of team member during the project | 3 | 0 | 3 |  | 1. Make sure every team member is familiar in all major and critical modules.
9 | Remote stations can be disconnected from network for any reason during system integration testing | 1 | 3 | 3.1623 |  | 1. Well plan for integration testing with remote stations. 2. Discuss with remote stations infrastructure team to execute test plans for all scenarios.
10 | Lack of knowledge on project business domain | 2 | 2 | 2.8284 |  | 1. Get detailed documentation from business user understand their business domain. 2. Face-to-Face discussion with business user
11 | Failure or laggy performance of application's end point api because of multiple requests from different remote stations at the same time. | 1 | 4 | 4.1231 |  | 1. In order to meet the performance requirement, it is better that we design the system well during the design stages 2. Try to involve some experts to design the architecture first 3. Ensure the sufficient loading and performance testing along the way 4. In case of encountering the performance issue, we try to tune performance immediately not till the end of the project.
12 | Misunderstanding of the client's requirement and implemented some functionlity wrongly | 3 | 2 | 3.6056 |  | 1. Requirement specification should be documented with all the scenarios and constraints. Before we start, all the changes should be documented and get proper sign off from user.

## Risk Check-Box List
Risk ID | Risk Item | Impact | [5 empty] | Likelihood | [5 empty] | Risk Score | Comments | Mitigation
Mitigation |  | Reduce Functionality 1 | Increased Cost 2 | Schedule Slippage 3 | Quality Cost 4 | Performance 5 | Total | Novelty 1 | Product History 2 | Project Team History 3 | Recognized Authority 4 | Expectation 5 | Total |  |  | Mitigation
1 | Complexity of System Interfaces - System Interface requiredments becomes complex to handle | x | x | x | - | x | 4 | x | - | - | x | x | 2 | 4.4721 | Understanding the no of interfaces with other systems and their requirements
2 | Technical Complexity - No of technical components that the team ha limited knowledge at this time | - | x | x | x | x | 4 | - | x | x | x | - | 3 | 5 | Understanding the technical complexity of the project and being able to deliver the project
3 | User Requirements to confirm the scope - Clarity on the scope and next level user requirements | x |  | x | x | x | 4 | - | - | - | x | x | 2 | 4.4721 | Finalization of User requirements
4 | Expectatations on the Real time Performance of the system | - | x | - | x | x | 3 | - | x | - | x | x | 3 | 4.2426 | Expectations on the systems performance(Real time)
5 | Hardware Technology adapted by the project | - | x | x | x | x | 4 | - | - | - | x | - | 1 | 4.1231 | Project team's familiarity of the Hardware Technology to be adapted by the proposed system
6 | Finalization of Project Plan | - | x | x | x | - | 3 | - | - | x | x | x | 3 | 4.2426 | Project Plan with Mile stones and expected deliverables agreed and accepted by relevant stakeholders
7 | Limited technical skill sets - cloud services - rich UI for real time analytic - LabView | - | - | x | - | x | 2 | x | - | - | - | - | 1 | 2.2361 |  | 1. Do some POC work to ensure the concepts is workable and doable 2. Consult some experts to get some idea
8 | Withdrawing of team member during the project | x |  | x | x |  | 3 | - | - | - | - | - | 0 | 3 |  | 1. Make sure every team member is familiar in all major and critical modules.
9 | Remote stations can be disconnected from network for any reason during system integration testing | - | - | x |  | - | 1 | x | - | - | x | x | 3 | 3.1623 |  | 1. Well plan for integration testing with remote stations. 2. Discuss with remote stations infrastructure team to execute test plans for all scenarios.
10 | Lack of knowledge on project business domain | - | - | x | x | - | 2 | - | - | x |  | x | 2 | 2.8284 |  | 1. Get detailed documentation from business user understand their business domain. 2. Face-to-Face discussion with business user
11 | Failure or laggy performance of application's end point api because of multiple requests from different remote stations at the same time. | - | - | - | - | x | 1 | x | x | - | x | x | 4 | 4.1231 |  | 1. In order to meet the performance requirement, it is better that we design the system well during the design stages 2. Try to involve some experts to design the architecture first 3. Ensure the sufficient loading and performance testing along the way 4. In case of encountering the performance issue, we try to tune performance immediately not till the end of the project.
12 | Misunderstanding of the client's requirement and implemented some functionlity wrongly | x |  | x |  | x | 3 | x | - | x | - | - | 2 | 3.6056 |  | 1. Requirement specification should be documented with all the scenarios and constraints. Before we start, all the changes should be documented and get proper sign off from user.