## Revision History
Software System Test Specification and Report
SERIS
SWSYS_TS - Description
Author : | Nay Lin Aung
Revision : | 1.1
Status : | Released
File : | SWSYS_TS.xlsx
History
Revision | Date | Author | Reason
Draft | 2018-08-16 | Nay Lin Aung | Draft version
1.1 | 2019-01-20 | Nay Lin Aung | Edited testcases and set baseline.
For internal use |  | Date | Department
Designed By | nelin.softcon@gmail.com | 2019-01-20 | Dept.Name
Released By | nelin.softcon@gmail.com | 2019-01-20 | QA
SERIS |  | Designation
SWSYS_TS

## System Test Specifications
Test ID | Test Objective | TestCaseID | TestCase Name | Tracebility | Priority | Input | Expected Result | Test Result | Remark | Pass | Fail | NoResult
Test-1 16-08-2018
T1 | Testing authentication of user into the system | T1.1 | Authentication test with correct user name and password | 3.2.2 | 1 | Pre-condition: Assume user account has already been created for this user. Key in registered user name and password. | Authentication should be successful and user should be able to login. | Pass
|  | T1.2 | Authentication test with incorrect user name and password | 3.2.2.2 | 1 | Key in incorrect user name and password. | Authentication should fail and access is denied.. | Pass
|  | T1.3 | Authentication test with incorrect user name. | 3.2.3.1 | 1 | Key in only incorrect user name and correct password. | Authentication should fail and access is denied. | Pass
|  | T1.4 | Authentication test with incorrect password. | 3.2.3.1 | 1 | Key in correct user name and incorrect password. | Authentication should fail and access is denied. | Pass
T2 | Testing on maintaining personas | T2.1 | Viewing users' personas | 3.2.3.1 | 1 | Pre-condition: Assume system user with admin-right has already logged into the system. User presses it account on user page. User clicks on persona drop-down list. | List of available personas should be displayed in the drop-down list. | Pass
|  | T2.2 | Viewing individual persona | 3.2.3.3 | 1 | Admin-user click on a particular user name from the list of users from user page. | It should go to respective page of particular user. The user's persona information should be displayed. | Pass
|  | T2.3 | Adding station for particular person | 3.2.3.5 | 1 | Click on a particular user name from the list of users from user page. Press "Select" button for adding new stations for the user and save. Press "Save" button. | New stations should have been added for the user. Otherwise, test fails. | Pass
|  | T2.4 | Removing station from particular person | 3.2.3.5 | 1 | Click on a particular user name from the list of users from user page. Press (x) beside station icon and save. | Alert message for confirmation should be popped up. If confirmed "yes",that particular station should be removed from the list. | Pass | Request message should be popped up for confirmation of removal.
|  | T2.5 | Creating new station | 3.2.3.5 | 1 | Navigate to Station page and press "Add" button. Key in new station name in the name field of the page and other information. Check and verify by navigating to station page. | A new station should have been added in the station list. | Pass | Are there any manual processes needed to be done like setting rules from AWS IoT core?
T3 | Test on maintaining users | T3.1 | Create user | 3.2..3.1 | 1 | Pre-condition: Assume system user with admin-right has already logged into the system. Key in user name, email ,password and relavant information for creating new user account and press "save" button. | There should be no error msg poping up. New user account should have been created.It should be verified by going to users page and check the list of users to confirm whether a new user account has been added. | Pass
|  | T3.2 | Update user information | 3.2..3.1 | 1 | 1) Go to users page and click on any user and update any field of that particular user's information and save. 2) Go back to users page and check that user's information again. | User information of that particular user should have been updated. | Pass
|  | T3.3 | View user information | 3.2..3.1 | 1 | Go to users page and click on a particular user. | Information of that user should be able to view. | Pass
|  | T3.4 | Reset password | 3.2.2.6 | 1 | 1) Go to users page and click on any user and update with new password in password field of that particular user's information and save. 2) User log out from the system and log in again using new password. | 2) User should be able to log in with new password. Otherwise , test fails. | NoResult
|  | T3.5 | Change access right | 3.2.2.6 | 1 | Assuming that current access right is admin-right: 1) Go to users page and change your own role as normal user's role in role field in user's information page and save. 2) Log out from the system and log in again. 3) Try to access pages intended for admin-right user. (create new user account). | Access should be denied when creating new user account which is only intended for admin user. | NoResult
|  | T3.6 | Deactivate account | 3.2.2.6 | 1 | 1) Log into the system using admin account. 2) Go to users page and select particular user. 3) Press "Deactivate" button. Popup alert appears for confirmation. 4) Press "yes" and log out from the system. 5) Log in the system using account name which has been deactivated previously. | 5) There should be authentication error and access should have been denied for that account. | NoResult
T5 | Testing on View/select user(s) | T4.1 | View list of users | 3.2.3.1 | 2 | Pre-condition: Assume system user with admin-right has already logged into the system. 1) Go to user page and check the list. | List of users should be able to be viewed. | Pass
|  | T4.2 | Select particular user for updating information | 3.2.3.1 | 2 | 1) Go to user list page and select a user for viewing its information. 2) Update any field of that particular user and save it. 3) Go to user list page and select the user for viewing its updated information. | 1) Updated information of that particular user should be available for viewing. | Pass
T7 | Testing on history record data | T5.1 | Checking history record | 3.2.7 | 1 | Assumption: The system already have some data relating to users, stations, etc in backend database. Go to history record page and view the record in graph. | There should be relavent data displayed in graph. | Pass
|  | T5.2 | Checking on automatic update of history record after editing and navigation | 3.2.5.2 | 2 | Edit any station name from station page and save it. Navigate back to history record page | .It should have fetched newly updated data and display it correctly. Otherwise, test fails. | Fail
T8 | Testing on Sending data | T7.1 | Sending data from device to AWS cloud IoT core |  | 1 | Pre-condition: Make sure that the systen is up and running, and able to send out data from sensors and devices 1)Monitor and check data stream sending from devices. (Visually, data can be monitored from Front-end browser since it is intended to view real time data.) | Front-end browser should be updating device data under test at one second interval. | NoResult
T10 | Testing on storing of structured data into database | T8.1 | Verification of correct storage of raw data and structured data in the cloud database | 3.2.5.1 | 1 |  |  | NoResult
T11 | Testing on sending of real-time data to synchronizer | T9.1 | Verification of sending real-time data to Synchronizer application | 3.2.5.1 | 1 |  |  | NoResult
T12 | Testing on synchronization of data with browsers | T10.1 | Checking functionality of viewing real-time data for particular device from web browser interface for monitoring | 3.2.6 | 1 |  |  | NoResult
T13 | Testing on getting device health status | T11.1 | Getting device health status |  |  |  |  | NoResult
T14 | Testing on downloading of history data | T12.1 | Downloading history data from the system | 3.2.5.2 | 1 | Press download icon from the left pane. Select station/stations from the list. | It should start downloading history data for selected station/stations. Otherwise test fails. | Fail | Downloading never end.
T15 | Testing on viewing real-time station information | T13.1 | Viewing real-time data from the station | 3.2.6 | 1 |  |  | NoResult
T16 | Testing on viewing history information of station | T14.1 | Viewing station history | 3.2.7 | 1 | Go to "History records" page and select a particular station and date. | I should show historical data for that particular station. Otherwise, test fails. | Pass
T17 | Testing on notification of device status | T15.1 | Notification of device status | 3.2.8 |  |  |  | NoResult
T25 | Testing on maintaining stations | T16.1 | Test for adding new station |  | 1 | Go to stations page and press "ADD" button. Key in all the necessary information and press "SAVE". | New station should have been added and shown on the station list. Otherwise test fails. | Pass
|  | T16.2 | Remove existing station |  | 1 | Go to station page and select a particular station for removal. | The station shoud have been removed from the list. Otherwise, test fails. | NoResult | Where is option for removal of the station.
T26 | Checking security behavior( Login and Logout) (Non-Functional) | T17.1 | Testing on Login. |  | 2 | Login using password for a particular user. | The user should be able to login. | Pass
|  | T17.2 | Testing on Logout |  | 2 | Current user logout from the system. | The user should logout from the system | Pass
|  | T17.3 | Testing for confirmation of actual logout for a particular user. |  | 2 | User login again using his own credential. User closes the browser without logging out. | N/A | NoResult
[6 empty] | The user opens the browser again using the web link(EC2). | It should be in main login page requesting user ID and password again. It should not be in dashboard page and the use should have not been logged in. Otherwise, test fails. | Fail | It seems there is problem in handling data in cloud cache.
|  | T18.4 | Testing on refreshing the page |  | 2 | After login, navigate the pages (dashboard, users, stations, etc.), and then press refresh button from the browser. | The browser should stay in current page with updated data after refreshing. It shouldn't have any errors. Otherwise, test fails. | Fail | "There was an unexpected error (type=Not Found, status=404)." Page showed error!
[7 empty] | Numbers of Passed Results | #REF!
[7 empty] | Numbers of Failed Results | #REF!
Numbers of No-Results