## RTM
Sl No | URS | Requirements | Use cases |  | Requirement model | Design model | Code implementation | Test cases | Remark
1 | 3.2.2 | User Login and Access Control | 3.10 | Login |  | 17 | Completed
2 | 3.2.2.2 | User/Access Control Mapping | 3.10 | Login |  | 17 | Completed
3 | 3.2.3.1 | User Management | 3.1 | Maintain user |  | 4 | Completed
4 | 3.2.3.1 | User Management | 3.4 | View/select users |  | 3 | Completed
5 | 3.2.3.3 | Persona | 3.7 | Add persona |  | 2 | Completed
6 | 3.2.3.4 | Station Management | 3.2 | Maintain station |  | 6 | Completed
7 | 3.2.3.4 | Station Management | 3.5 | View/select stations |  | 5 | Completed
8 | 3.2.3.5 | User/Station Mapping | 3.2 | Maintain station |  | 6 | Completed
9 | 3.2.3.6 | Forgot Password | 3.11 | Forgot password |  | 15 | Completed
10 | 3.2.3.6 | Forgot Password | 3.12 | Reset password |  | 16 | Completed
11 | 3.2.5.2 | Data Download | 3.16 | Download history data |  | 13 | Completed
12 | 3.2.5.2 | Data Download | 3.18 | Submit downlaod request |  | 12 | Completed
13 | 3.2.5.2 | Data Download | 3.19 | Generate downlaod file |  | 19 | Completed
14 | 3.2.5 | Central Data Maagement | 3.20 | Clean old fast data |  | 18 | Completed
15 | 3.2.5.1 | Data Capture | 3.8 | Send data |  | 20 | Completed
16 | 3.2.5.1 | Data Capture | 3.9 | Upload batch data |  | 21 | Completed
17 | 3.2.6 | Real time dashboard | 3.13 | Monitor station data |  | 9 | Completed
18 | 3.2.6 | Real time dashboard | 3.14 | Monitor station health |  | 10 | Completed
19 | 3.2.7 | Reports | 3.17 | View station history information |  | 11 | Completed
20 | 3.2.8 | System Alert and Notifications | 3.15 | Submit error report |  | 14 | Completed
21 | 3.2.8 | System Alert and Notifications | 3.6 | View/select error report |  | 7 | Completed
22 | 3.2.8 | System Alert and Notifications | 3.3 | Close error report |  | 8 | Completed
23 | 3.2.9 | Auditing & Traceability
24
25

## References
Code implementation status | Use case status
Pending | Pending
In progress | In progress
Completed | Completed
Revising on feedback