## WBS
# |  | Task | Agnes | Bala | KM | NL | Tresa | William | Sponsor
1 |  | Project Initiation
| 1.1 | Setup project filing system |  |  |  | x
| 1.2 | Project requirement gathering | x |  | x |  | x |  | x
| 1.3 | Project risk tracker |  | x
| 1.4 | Prepare WBS |  |  | x
| 1.5 | Produce project plan document |  |  | x
| 1.6 | Review/Finalize project plan document |  | x |  | x | x | x | x
| 1.7 | Produce quality plan |  |  |  | x
| 1.8 | Review/Finalize quality plan | x | x | x | x | x | x
| 1.9 | Produce User requirement specification |  | x
| 1.10 | Review/Finalize User requirement specification |  |  | x | x | x | x | x
| 1.11 | Produce Use Case Modelling survey report |  |  | x
| 1.12 | Review/Finalize Use Case Modelling survey report |  | x |  | x | x | x | x
| 1.13 | Produce User Interface Speficication 1 |  |  |  | x
| 1.14 | Review/Finalize User Interface Specification |  | x |  |  | x | x
| 1.15 | Produce High Level Design Specification |  |  |  |  | x
| 1.16 | Review/Finalize High Level Design Specification |  |  | x |  |  | x | x
| 1.17 | Exploring AWS services | [5 empty] | x
2 |  | Build Prototype
| 2.1 | Prepare prototype |  |  | x |  | x | x
| 2.2 | Test prototype |  | x |  | x
| 2.3 | Produce Prototype Study Report | [5 empty] | x
| 2.4 | Review/Finalize Prototype Study Report |  | x |  |  | x
3 |  | Incorporate Audit Feedbacks
| 3.1 | Revised on Audit Comments |  | x | x | x | x | x
| 3.2 | Prepare for presentation |  | x | x | x | x | x
4 |  | Analysis and Design Modelling (Increment 1)
| 4.1 | Produce Use Case Model Survey Report (Requirement) |  |  | x |  | x
| 4.2 | Review/FinaliseUse Case Model Survey Report (Requirement) |  | x
| 4.3 | Identify Domain Objects/Attributes |  | x |  | x |  | x
| 4.4 | Produce Class Diagrams |  |  | x |  | x
| 4.5 | Produce Sequence Diagrams |  | x | x | x | x
| 4.6 | Produce Design Model Report |  | x |  |  |  | x
| 4.7 | Review/FinaliseDesign Model Report |  | x | x | x | x
5 |  | Implementation & Coding
| 5.1 | Setup necessary cloud environment |  |  |  | x |  | x
| 5.2 | Source control plan and setup |  |  | x | x | x
| 5.3 | Backend coding |  |  |  |  | x | x
| 5.4 | Frontend coding |  | x | x
| 5.5 | Unit testing |  | x | x |  | x | x
| 5.6 | Peer review coding |  | x | x |  | x | x
6 |  | Testing
| 6.1 | Produce System Test Plan |  |  |  | x
| 6.2 | Review/FinaliseSystem Test Plan |  | x | x | x | x | x
| 6.3 | Perform System Testing |  | x | x | x | x | x
| 6.4 | Bug Review/Corrective action/Rework |  | x | x | x | x | x
| 6.5 | Prepare SIT Document |  |  |  | x
| 6.6 | Review/FinaliseSIT Document |  | x | x | x | x | x
| 6.7 | Prepare User Acceptance Test Plan |  |  |  | x
| 6.8 | Review/FinaliseAcceptance Test Plan |  | x | x | x | x | x
| 6.9 | Perform Integration Testing |  | x | x | x | x | x
| 6.10 | Review Test Result and perform Corrective Action |  | x | x | x | x | x
| 6.11 | End User Training Manual and Write User Guide |  |  |  | x
| 6.12 | Review/FinaliseUser Guide |  | x | x | x | x | x
| 6.13 | Perform User Acceptance Testing |  | x | x | x | x | x | x
| 6.14 | Review Acceptance Test Result/Corrective Action |  | x | x | x | x | x
| 6.15 | Prepare User Acceptance Test Document |  |  |  | x
| 6.16 | Review/FinaliseUser Acceptance Test Document |  | x | x | x | x | x
7 |  | Revised Documentation for 2nd Audit
| 7.1 | Revised High Level Design Specification |  |  |  |  | x
| 7.2 | Revised Project Plan |  |  | x
8 |  | Incorporate Audit Feedbacks
| 8.1 | Revised on Audit Comment |  |  |  | x
| 8.2 | Prepare for Presentation |  | x | x | x | x | x
9 |  | Analysis and Design Modelling (Increment 2)
| 9.1 | Produce Use Case Model Survey Report (Requirement) |  |  | x |  | x
| 9.2 | Review/FinaliseUse Case Model Survey Report (Requirement) |  | x
| 9.3 | Identify Domain Objects/Attributes |  | x |  | x |  | x
| 9.4 | Produce Class Diagrams |  |  | x |  | x
| 9.5 | Produce Sequence Diagrams |  | x | x | x | x | x
| 9.6 | Produce Design Model Report |  | x |  |  |  | x
| 9.7 | Review/FinaliseDesign Model Report |  | x | x | x | x | x
10 |  | Programming (Increment 2)
| 10.1 | Backend coding |  |  |  |  | x | x
| 10.2 | Frontend coding |  | x | x
| 10.3 | Unit Testing |  | x | x |  | x | x
| 10.4 | Peer Review of Coding |  | x | x |  | x | x
11 |  | Testing (Increment 2)
| 11.1 | Produce System Test Plan |  |  |  | x
| 11.2 | Review/FinaliseSystem Test Plan |  | x | x | x | x | x
| 11.3 | Perform System Testing |  | x | x | x | x | x
| 11.4 | Bug Review/Corrective action/Rework |  | x | x | x | x | x
| 11.5 | Prepare SIT Document |  |  |  | x
| 11.6 | Review/FinaliseSIT Document |  | x | x | x | x | x
| 11.7 | Prepare User Acceptance Test Plan |  |  |  | x
| 11.8 | Review/FinaliseAcceptance Test Plan |  | x | x | x | x | x
| 11.9 | Perform Integration Testing |  | x | x | x | x | x
| 11.10 | Review Test Result and perform Corrective Action |  | x | x | x | x | x
| 11.11 | End User Training Manual and Write User Guide |  |  |  | x
| 11.12 | Review/FinaliseUser Guide |  | x | x | x | x | x
| 11.13 | Perform User Acceptance Testing |  | x | x | x | x | x | x
| 11.14 | Review Acceptance Test Result/Corrective Action |  | x | x | x | x | x
| 11.15 | Prepare User Acceptance Test Document |  |  |  | x
| 11.16 | Review/FinaliseUser Acceptance Test Document |  | x | x | x | x | x
12 |  | Implementation
| 12.1 | Source Deployment Process Guide |  |  |  | x
| 12.2 | AWS setup and manual |  |  | x |  | x | x
| 12.3 | Release Project |  |  | x
| 12.4 | Prepare User Training |  | x | x | x | x | x
| 12.5 | Training User |  |  | x |  | x | x | x
| 12.6 | Revised Documents and Sign-Off |  | x |  | x
| 12.7 | Project Hand-over |  | x | x | x | x | x | x
13 |  | Incorporate Audit Feedbacks
| 13.1 | Revised on Audit Comment |  | x | x | x | x | x
| 13.2 | Prepare for Presentation |  | x | x | x | x | x

## Milestones
Project Milestones |  | Approx. Date
Increment 0
1.1 | Issue Work Breakdown Structure | 2018-03-06
1.2 | Issue Use Case Modelling Survey Report | 2018-03-28
1.3 | Issue Prototype Study Report | 2018-04-15
1.4 | Issue Risk Tracker | 2018-03-15
1.5 | Issue Project Plan Doc | 2018-04-12
1.6 | Issue User Requirement Specification Doc | 2018-04-15
1.7 | Issue User Interface Specification Doc | 2018-04-17
1.8 | Issue High Level Design Doc | 2018-04-14
1.9 | Issue Quality Plan Doc | 2018-04-14
1.10 | Implement Prototype | 2018-04-15
Increment 1
2.1 | Setup Cloud Environment | 2018-05-02
2.2 | Issue Use Case Modelling Survey Report(Analysis) | 2018-05-06
2.3 | Issue Design Report | 2018-05-20
2.4 | Complete Source Control Plan and Setup | 2018-05-01
2.5 | Complete Coding | 2018-07-15
2.6 | Issue System Test Plan | 2018-05-20
2.7 | Complete System Testing | 2018-07-22
2.8 | Complete Integration Test | 2018-07-29
2.9 | Issue SIT Document | 2018-08-05
2.10 | Issue User Acceptance Test Plan | 2018-08-05
2.11 | Issue End User Traning Manual and User Guide | 2018-08-12
2.12 | Complete User Acceptance Testing | 2018-08-19
2.13 | Issue User Acceptance Test Document | 2018-07-25
Increment 2
3.1 | Setup Cloud Environment | 2018-09-02
3.2 | Issue Use Case Modelling Survey Report(Analysis) | 2018-09-09
3.3 | Issue Design Report | 2018-09-16
3.4 | Complete Source Control Plan and Setup | 2018-09-02
3.5 | Complete Coding | 2018-11-18
3.6 | Issue System Test Plan | 2018-11-23
3.7 | Complete System Testing | 2018-11-25
3.8 | Complete Integration Test | 2018-12-02
3.9 | Issue SIT Document | 2018-12-09
3.10 | Issue User Acceptance Test Plan | 2018-12-09
3.11 | Issue End User Traning Manual and User Guide | 2018-12-16
3.12 | Complete User Acceptance Testing | 2018-12-09
3.13 | Issue User Acceptance Test Document | 2018-12-16
3.14 | Complete AWS setup and manual | 2018-12-23
3.15 | Commence User Traning | 2018-12-23
3.16 | Project Hand-over | 2018-12-31