## Ctrl-Track
Task Name | Duration | Start | Finish | Work (hrs) (Planned) | % Complete | Earned Value (Earned) | (BTC) To be performed | Reported (Actual)
Project Initiation | 52 days | Thu 01-02-18 | Fri 13-04-18 | 428 | 100% | 428 | 0
Build Prototype | 9 days | Mon 16-04-18 | Thu 26-04-18 | 50 | 100% | 50 | 0
Incorporate Audit Feedbacks | 4 days | Fri 27-04-18 | Wed 02-05-18 | 40 | 100% | 40 | 0
Analysis and Design Modelling (Increment 1) | 32 days | Thu 03-05-18 | Fri 15-06-18 | 294 | 100% | 294 | 0
Implementation & Coding | 52 days | Thu 10-05-18 | Fri 20-07-18 | 226 | 100% | 226 | 0
Testing | 51 days | Mon 18-06-18 | Mon 27-08-18 | 306 | 100% | 306 | 0
Revised Documentation for 2nd Audit | 1 day | Tue 28-08-18 | Tue 28-08-18 | 4 | 100% | 4 | 0
Incorporate Audit Feedbacks | 4 days | Tue 28-08-18 | Fri 31-08-18 | 32 | 100% | 32 | 0
Analysis and Design Modelling (Increment 2) | 32 days | Mon 03-09-18 | Tue 16-10-18 | 294 | 100% | 294 | 0
Programming (Increment 2) | 30 days | Wed 17-10-18 | Tue 27-11-18 | 240 | 100% | 240 | 0
Testing (Increment 2) | 55 days | Wed 17-10-18 | Tue 01-01-19 | 306 | 95% | 290.7 | 15.3
Implementation | 41 days | Wed 21-11-18 | Wed 16-01-19 | 106 | 86% | 91.16 | 14.84
Incorporate Audit Feedbacks | 4 days | Thu 17-01-19 | Tue 22-01-19 | 32 | 88% | 28.16 | 3.84
|  |  |  | 2358 | hours | 2324.02 | 33.98 | 2361
|  |  |  | 294.75 | man days | 290.5025 | 4.2475 | 295.125
| Planned: pp mds (6 member team) |  |  | 49.125 | man days
| Revised: pp mds (5 member team) |  |  | 58.95
| As of now: pp mds (4 member team) |  |  | 73.6875 | man days
| As of now: Each team member (hours) |  |  | 589.5 | hours
Task Name | Duration | Start | Finish | Work (hrs) | % Complete | Earned Value
Project Initiation | 52 days | Thu 01-02-18 | Fri 13-04-18 | 428 hrs | 100%
Build Prototype | 9 days | Mon 16-04-18 | Thu 26-04-18 | 50 hrs | 100%
Incorporate Audit Feedbacks | 4 days | Fri 27-04-18 | Wed 02-05-18 | 40 hrs | 100%
Analysis and Design Modelling (Increment 1) | 32 days | Thu 03-05-18 | Fri 15-06-18 | 294 hrs | 97%
Implementation & Coding | 52 days | Thu 10-05-18 | Fri 20-07-18 | 226 hrs | 97%
Testing | 51 days | Mon 18-06-18 | Mon 27-08-18 | 306 hrs | 22%
Revised Documentation for 2nd Audit | 1 day | Tue 28-08-18 | Tue 28-08-18 | 4 hrs | 75%
Incorporate Audit Feedbacks | 4 days | Tue 28-08-18 | Fri 31-08-18 | 32 hrs | 81%
Analysis and Design Modelling (Increment 2) | 32 days | Mon 03-09-18 | Tue 16-10-18 | 294 hrs | 0%
Programming (Increment 2) | 30 days | Wed 17-10-18 | Tue 27-11-18 | 240 hrs | 0%
Testing (Increment 2) | 55 days | Wed 17-10-18 | Tue 01-01-19 | 306 hrs | 0%
Implementation | 41 days | Wed 21-11-18 | Wed 16-01-19 | 112 hrs | 0%
Incorporate Audit Feedbacks | 4 days | Thu 17-01-19 | Tue 22-01-19 | 40 hrs | 0%

## Reported
Reporting Period | Total | Bala | KM | William | Nay | Treza | Agnes | Remarks | Reporting Period | 2018-02-01 | 2018-03-01 | 2018-04-01 | 2018-05-01 | 2018-06-01 | 2018-07-01 | 2018-08-01 | Total
2018-02-01 | 162 | 12 | 30 | 30 | 25 | 30 | 35 |  | Clocked | 162 | 243 | 212 | 114 | 115 | 140 | 160 | 1186
2018-03-01 | 243 | 40 | 41 | 41 | 40 | 40 | 41
2018-04-01 | 212 | 44 | 38 | 51 | 40 | 39 |  | Agnes withdrawn | Reporting Period | Upto Aug-2018 | 2018-09-01 | 2018-10-01 | 2018-11-01 | 2018-12-01 | 2019-01-01 | 2019-02-01 | Total
2018-05-01 | 114 | 13 | 35 | 41 | 0 | 25 |  |  | Clocked | 1186 | 175 | 179 | 224 | 257 | *340 | *40 | 2401
2018-06-01 | 115 | 20 | 30 | 30 | 20 | 15 |  | Treza Withdrawn | [6 empty] | (tentative) | (planned)
2018-07-01 | 140 | 30 | 40 | 35 | 25 | 10
2018-08-01 | 200 | 43 | 60 | 63 | 34
2018-09-01
2018-10-01
2018-11-01
2018-12-01 | [9 empty] | 0
2018-09-01 | 175 | 35 | 50 | 40 | 50
2018-10-01 | 179 | 45 | 50 | 39 | 45
2018-11-01 | 224 | 80 | 60 | 34 | 50
2018-12-01 | 257 | 80 | 59 | 68 | 50
2019-01-01 | 340 | 90 | 90 | 90 | 70 |  |  | *tentative
2019-02-01 | 40 | 10 | 10 | 10 | 10 |  |  | *planned
Total | 2401 | 542 | 593 | 572 | 459 | 159 | 76 | hours
| 300.125 | 67.75 | 74.125 | 71.5 | 57.375 | 19.875 | 9.5 | man days

## WBS (Outstadning tasks)
% Complete | Task Name | Duration | Start | Finish | Work | Complete (hrs) | Remaning (hrs)
95% | Testing (Increment 2) | 55 days | Wed 17-10-18 | Tue 01-01-19 | 306 hrs | 290.7 | 15.3
50% | End User Training Manual and Write User Guide | 5 days | Wed 07-11-18 | Tue 13-11-18 | 10 hrs | 5 | 5
50% | Review/FinaliseUser Guide | 2 days | Fri 21-12-18 | Mon 24-12-18 | 20 hrs | 10 | 10
86% | Implementation | 41 days | Wed 21-11-18 | Wed 16-01-19 | 106 hrs | 91.16 | 14.84
80% | Source Deployment Process Guide | 5 days | Wed 21-11-18 | Tue 27-11-18 | 10 hrs | 8 | 2
90% | AWS setup and manual | 2 days | Wed 02-01-19 | Thu 03-01-19 | 12 hrs | 10.8 | 1.2
75% | Release Project | 1 day | Fri 11-01-19 | Fri 11-01-19 | 2 hrs | 1.5 | 0.5
80% | Revised Documents and Sign-Off | 2 days | Wed 02-01-19 | Thu 03-01-19 | 8 hrs | 6.4 | 1.6
80% | Project Hand-over | 3 days | Mon 14-01-19 | Wed 16-01-19 | 36 hrs | 28.8 | 7.2
88% | Incorporate Audit Feedbacks | 4 days | Thu 17-01-19 | Tue 22-01-19 | 32 hrs | 28.16 | 3.84
75% | Revised based on Audit Comment | 2 days | Thu 17-01-19 | Fri 18-01-19 | 16 hrs | 12 | 4
[5 empty] | Hours | 2324.02 | 33.98
[5 empty] | Percentage | 98.56% | 1.441%

## Status Tracking
% Complete | Task Name | Duration | Start | Finish | Work | Complete (hrs) | Remaning (hrs)
100% | Project Initiation | 52 days | Thu 01-02-18 | Fri 13-04-18 | 428 hrs | 428 | 0
100% | Build Prototype | 9 days | Mon 16-04-18 | Thu 26-04-18 | 50 hrs | 50 | 0
100% | Incorporate Audit Feedbacks | 4 days | Fri 27-04-18 | Wed 02-05-18 | 40 hrs | 40 | 0
100% | Analysis and Design Modelling (Increment 1) | 32 days | Thu 03-05-18 | Fri 15-06-18 | 294 hrs | 294 | 0
100% | Implementation & Coding | 52 days | Thu 10-05-18 | Fri 20-07-18 | 226 hrs | 226 | 0
100% | Testing | 51 days | Mon 18-06-18 | Mon 27-08-18 | 306 hrs | 306 | 0
100% | Revised Documentation for 2nd Audit | 1 day | Tue 28-08-18 | Tue 28-08-18 | 4 hrs | 4 | 0
100% | Incorporate Audit Feedbacks | 4 days | Tue 28-08-18 | Fri 31-08-18 | 32 hrs | 32 | 0
100% | Analysis and Design Modelling (Increment 2) | 32 days | Mon 03-09-18 | Tue 16-10-18 | 294 hrs | 294 | 0
100% | Programming (Increment 2) | 30 days | Wed 17-10-18 | Tue 27-11-18 | 240 hrs | 240 | 0
95% | Testing (Increment 2) | 55 days | Wed 17-10-18 | Tue 01-01-19 | 306 hrs | 290.7 | 15.3
86% | Implementation | 41 days | Wed 21-11-18 | Wed 16-01-19 | 106 hrs | 91.16 | 14.84
88% | Incorporate Audit Feedbacks | 4 days | Thu 17-01-19 | Tue 22-01-19 | 32 hrs | 28.16 | 3.84
[5 empty] | Hours | 2324.02 | 33.98
[5 empty] | Percentage | 98.56% | 1.441%