## Risk Register
Sr No. | Risk Item | Control type | Specific Detail | Classification | Overall Impact | Event/Trigger Point | Action Owner | Status | Action taken
1 | As a part time student, challenging to find free common time slots to meet up therefore likely to miss scheduled milestones | Risk Minimisation | We divide and conquer the tasks into smaller tasks so that we spend a minimal hours per day on a regular basis | Project Team | 2B | (NA)Whenever it occurs | Project Manager |  | Collect details of Planned leave and backup plans from team members
2 | Delay in obtaining concrete requirements because of the same being unclear and vague, thus, delay in URS planned schedule | Risk Avoidance/Removal | Regular meetings with client to clarify requirements | Technical | 3B | New Requirements after requirement sign off | Project Manager |  | Baselining URS
3 | Project team is not familiar with AWS landscape because it is a new technology hence we foresee delay in design and implementation | Risk Minimisation and Localisation | Prototyping with AWS, study on AWS to support our architectural design | Technical | 4B | Development phase | Project Leader
4 | Agnes has withdrwan from the FYP. Were informed sometime towards the end of Mar. The URS is due to be shared with the client in the 1st week of April | Risk Minimisation | The URS/current work-stream and artefcat that Agnes was managing at that time has been re-assigned with in the team | Project Team | 3B | Requirements Study Phase | Bala | Closed | Bala took over the URS preparation and reviewed it within the team, before being circulated to the client
5 | There could be unknown issues arising while capturing data from actual device | Risk Minimisation and Localisation | In the proto type, the windows machine is as acting as the device and sending signals. | Technical | 4B | Development phase | Project Leader |  | Request SERIS to provide us data samples. Request SERIS tp help cnfigure a device to send data to RAM proto type
6 | Another team member withdrawing from the project team | Risk Minimisation | If the team loses one more member then it can become catastrophic at this juncture | Project Team | 4B | (NA)Whenever it occurs | Project Manager
7 | As per requirement and current design there is a need for lambda to send data back to browser in real-time. Only after sizing this can be confirmed (No of Stations/Devices & Streaming Frequency) | Risk Minimisation and Localisation | In the proto type, the windows machine is as acting as the device and sending limited set of data signals. | Technical | 4B | Development phase | Project Leader |  | Request SERIS to share the detailed requirements along with data samples. Besides the no of devices and expected throughput from the RAM application
8
9
10
11
12
13

## Version History
Version | Creator | Reviewer/Approver | Date | Amendment Description
0.1 | Balasubramanian Narasimhan |  | 2018-03-28 | Intial Document
0.2 | Balasubramanian Narasimhan |  | 2018-05-08 | Revise and incorporate audit comments
0.3
0.4
0.5
0.6
0.7
0.8
0.9
1
1.1
1.1
1.2

## Risk Assessment Matrix
Appendix A – Example Risk Assessment Matrix
Risk Proberbality | Risk Serverity
| Catastrophic A | Critical B | Moderate C | Minor D | Negligible E
5- Frequent | 5A | 5B | 5C | 5D | 5E
4- Likely | 4A | 4B | 4C | 4D | 4E
3- Occassional | 3A | 3B | 3C | 3D | 3E
2-Seldom | 2A | 2B | 2C | 2D | 2E
1-Improable | 1A | 1B | 1C | 1D | 1E
Assessment Risk Index |  | Criteira |  |  | Accountable Organization
5A, 5B, 5C, 4A, 4B, 3A |  | Unacceptable under existing circumstances requires immediate action |  |  | Safety, Security, Quality & Environment
5D, 5E, 4C, 3B, 3C, 2A, 2B |  | Manageable under risk control & mitigation & management decision |  |  | Project Directors
4D, 4E, 3D, 2C, 1A, 1B |  | Acceptable after review of the operation. Requires continued tracking and recorded action plans. |  |  | Project Directors, Managers and /or Accountable Org. Levels
3E, 2D, 2E, 1C, 1D, 1E |  | Acceptable with continued data collection and trending for continuous improvement. |  |  | Project Sponsors and / or Accountable Org. Levels
Probability of Occurrences
Qualitative definition | Meaning |  |  |  |  | Value
Frequent | i) Likely to occur many times (occurred frequently) ii) Will be continuously experienced unless action is taken to change events |  |  |  |  | 5
Likely | i) Likely to occur some times (occurred infrequently) ii) The activity or event expected to occur 50-99% of the time. iii) Will occur often if events follow normal patterns of process or procedure. The event is repeatable and less sporadic iv) Auditor / Regulator likely to identify issue with minimal audit activity Process performance failures evident to trained auditors or regulators |  |  |  |  | 4
Occasional | i) Unlikely, but possible to occur (occurred rarely) ii) An activity or event occurs infrequently, or irregularly, or 25-50% of the time iii) Potential for infrequent occurrence. Events are sporadic in nature iv) Auditor / Regulator have potential of issue discovery during focused or specialized review. v) Process has higher degree of latent system errors discovered with adequate controls |  |  |  |  | 3
Seldom | i) Very unlikely to occur (not known it has occurred ) ii) An activity or event that occurs intermittently, or 1-25% of time iii ) Not likely to happen (but could) iv) Regulator / Auditor have low likelihood of issue identification during any general or focused review |  |  |  |  | 2
Improbable | i) A remote likelihood, being almost inconceivable that event will occur |  |  |  |  | 1

## Risk Assessment
Risk ID | Risk Item | Impact | [5 empty] | Likelihood | [5 empty] | Risk Score | Comments | Mitigation
Mitigation |  | Reduce Functionality 1 | Increased Cost 2 | Schedule Slippage 3 | Quality Cost 4 | Performance 5 | Total | Novelty 1 | Product History 2 | Project Team History 3 | Recognized Authority 4 | Expectation 5 | Total |  |  | Mitigation
1 | Complexity of System Interfaces - System Interface requiredments becomes complex to handle | x | x | x | - | x | 4 | x | - | - | x | x | 2 | 4.4721 | Understanding the no of interfaces with other systems and their requirements
2 | Technical Complexity - No of technical components that the team ha limited knowledge at this time | - | x | x | x | x | 4 | - | x | x | x | - | 3 | 5 | Understanding the technical complexity of the project and being able to deliver the project
3 | User Requirements to confirm the scope - Clarity on the scope and next level user requirements | x |  | x | x | x | 4 | - | - | - | x | x | 2 | 4.4721 | Finalization of User requirements
4 | Expectatations on the Real time Performance of the system | - | x | - | x | x | 3 | - | x | - | x | x | 3 | 4.2426 | Expectations on the systems performance(Real time)
5 | Hardware Technology adapted by the project | - | x | x | x | x | 4 | - | - | - | x | - | 1 | 4.1231 | Project team's familiarity of the Hardware Technology to be adapted by the proposed system
6 | Finalization of Project Plan | - | x | x | x | - | 3 | - | - | x | x | x | 3 | 4.2426 | Project Plan with Mile stones and expected deliverables agreed and accepted by relevant stakeholders
7 | Limited technical skill sets - cloud services - rich UI for real time analytic - LabView | - | - | x | - | x | 2 | x | - | - | - | - | 1 | 2.2361 |  | 1. Do some POC work to ensure the concepts is workable and doable 2. Consult some experts to get some idea
8 | Withdrawing of team member during the project | x |  | x | x |  | 3 | - | - | - | - | - | 0 | 3 |  | 1. Make sure every team member is familiar in all major and critical modules.
9 | Remote stations can be disconnected from network for any reason during system integration testing | - | - | x |  | - | 1 | x | - | - | x | x | 3 | 3.1623 |  | 1. Well plan for integration testing with remote stations. 2. Discuss with remote stations infrastructure team to execute test plans for all scenarios.
10 | Lack of knowledge on project business domain | - | - | x | x | - | 2 | - | - | x |  | x | 2 | 2.8284 |  | 1. Get detailed documentation from business user understand their business domain. 2. Face-to-Face discussion with business user
11 | Failure or laggy performance of application's end point api because of multiple requests from different remote stations at the same time. | - | - | - | - | x | 1 | x | x | - | x | x | 4 | 4.1231 |  | 1. In order to meet the performance requirement, it is better that we design the system well during the design stages 2. Try to involve some experts to design the architecture first 3. Ensure the sufficient loading and performance testing along the way 4. In case of encountering the performance issue, we try to tune performance immediately not till the end of the project.
12 | Misunderstanding of the client's requirement and implemented some functionlity wrongly | x |  | x |  | x | 3 | x | - | x | - | - | 2 | 3.6056 |  | 1. Requirement specification should be documented with all the scenarios and constraints. Before we start, all the changes should be documented and get proper sign off from user.