## Risk Register
Sl. No | Risk Item | Control type | Specific Detail | Classification | Overall Impact | Event/Trigger Point | Action Owner | Status | Action taken
1 | As we are engaged full-time in the office, Quiet challenging to meet up face-2-face at regular intervals impacting on meeting the scheduled milestones | Risk Minimisation | Catch-up and review regularly duing saturdays and having regular conf. calls. When required we re-distrubute and manage the tasks based on the current workload of the team members | Project Team | 2B | (NA)Whenever it occurs | Project Manager | Open | Keep track of upcoming and planned leaves of the team members
2 | Delay in obtaining concrete requirements because of the same being unclear and vague, thus, delay in URS planned schedule | Risk Avoidance/Removal | Regular meetings with client to clarify requirements | Technical | 3B | New Requirements after requirement sign off | Project Manager | Closed | Baselining URS; 5-Sep the URS was baselined
3 | Project team is not familiar with technical landscape because it is a new technology hence we foresee delay in design and implementation | Risk Minimisation and Localisation | The technical landscape is new to the entire team, and requires each one of us to undertstand the teachnicalities to contribute effectively to the project | Technical | 4B | Analysis phase | Project Leader | Closed | Prototyping by simulation, study on AWS, to support our architectural design. Consultantion with AWS experts to validate on the suitability of the proposed design
4 | Agnes has withdrwan from the FYP. Were informed sometime towards the end of Mar. The URS is due to be shared with the client in the 1st week of April | Risk Minimisation | The URS/current work-stream and artefcat that Agnes was managing at that time has been re-assigned with in the team | Project Team | 3B | Requirements Study Phase | Bala | Closed | Bala took over the URS preparation and reviewed it within the team, before being circulated to the client
5 | As per requirement and current design there is a need for lambda to send data back to browser in real-time. Only after sizing this can be confirmed (No of Stations/Devices & Streaming Frequency) | Risk Minimisation and Localisation | In the proto type, the windows machine is as acting as the device and sending limited set of data signals. | Technical | 4B | Development phase | Project Leader | Closed | Request SERIS to share the detailed requirements along with data samples. Besides the no of devices and expected throughput from the RAM application; SERIS requested us to perform simulation testing
6 | Project team can't spend enough time in project work due to examination preparation in June hence wouldn't be able to meet the planned schedule. | Risk Insurance | Team spent time for exam preparation and could not allocation enough time for Coding and Unit Testing. | Project Team | 4B | Exam Preparation | All | Closed | As a team, we understood the delay and the reason for it. Team is committed to spend extra effort in the month of July to catch up with the schedule
7 | Project team unable to visualize beyond a certain point on the system landscape, leading to re-work on the design | Risk Acceptance | Team as such had not thought through the end-to-end architecture and design and firm it up, due to uncertainities raised as we navigate through next level of details | Project Team | 4B | Re-work on the design | Project Manager | Closed | Requesting the client to provide us with actual/physical devices so as to get a practical understanding while mapping the functionalities and planning for activities beyond coding; The URS was bsaedline on 5-Sep, except for a few components to be addressed in Iteration-2
8 | There could be unknown issues arising while capturing data from actual device/station | Risk Minimisation and Localisation | In the proto type, the windows machine is as acting as the device and sending signals. | Technical | 4B | Development phase | Project Leader | Closed | Request SERIS to provide us data samples. Request SERIS to help cnfigure a device to send data to RAM proto type
9 | Another team member withdrawing from the project team | Risk Minimisation | If the team loses one more member then it can become catastrophic at this juncture | Project Team | 4B | (NA)Whenever it occurs | Project Manager | Closed | Risk triggered in Oct and accepted by the team; The team decided to split the workload of the team member who left
10 | Client has asked us to look in to the possibility of taking in JSON format data | Risk Acceptance | if there is a change in the source data feed, it will have a greater end-to-end to the project. | Project Team | 3A | Stakeholder engagement, Oct-2018 | All | Closed | However this means there is a considerable re-work from URS all the way into testing which has already been completed for and until increment-1. The team agreed to accept the risk in the best interest of meeting client requirements as they fit is best for their use case.
11 | There may be change from the current Elasticsearch to DynamoDB in the future (15-Dec-2018) |  | So some of the current codes are written only for current NoSQL db/ElasticSearch. In which case, Those codes have to be written to change to support the new NoSQL db/dynamoDB (15-Dec-2018) | Project Team | 3A | Stakeholder engagement, Dec/Jan-2018 | All | Closed | UAT sign-off received on 24-Jan-2019
12
13
14
15

## Risk Assessment Matrix
Appendix A – Example Risk Assessment Matrix
Risk Proberbality | Risk Serverity
| Catastrophic A | Critical B | Moderate C | Minor D | Negligible E
5- Frequent | 5A | 5B | 5C | 5D | 5E
4- Likely | 4A | 4B | 4C | 4D | 4E
3- Occassional | 3A | 3B | 3C | 3D | 3E
2-Seldom | 2A | 2B | 2C | 2D | 2E
1-Improable | 1A | 1B | 1C | 1D | 1E
Probability of Occurrences | Value | Meaning
Frequent | 5 | i) Likely to occur many times (occurred frequently) ii) Will be continuously experienced unless action is taken to change events
Likely | 4 | i) Likely to occur some times (occurred infrequently) ii) The activity or event expected to occur 50-99% of the time. iii) Will occur often if events follow normal patterns of process or procedure. The event is repeatable and less sporadic
Occasional | 3 | i) Unlikely, but possible to occur (occurred rarely) ii) An activity or event occurs infrequently, or irregularly, or 25-50% of the time iii) Potential for infrequent occurrence. Events are sporadic in nature
Seldom | 2 | i) Very unlikely to occur (not known it has occurred ) ii) An activity or event that occurs intermittently, or 1-25% of time iii ) Not likely to happen (but could)
Improbable | 1 | i) A remote likelihood, being almost inconceivable that event will occur
Assessment Risk Index | Criteira |  |  |  | Accountable Organization
5A, 5B, 5C, 4A, 4B, 3A | Unacceptable under existing circumstances requires immediate action |  |  |  | Safety, Security, Quality & Environment
5D, 5E, 4C, 3B, 3C, 2A, 2B | Manageable under risk control & mitigation & management decision |  |  |  | Project Directors
4D, 4E, 3D, 2C, 1A, 1B | Acceptable after review of the operation. Requires continued tracking and recorded action plans. |  |  |  | Project Directors, Managers and /or Accountable Org. Levels
3E, 2D, 2E, 1C, 1D, 1E | Acceptable with continued data collection and trending for continuous improvement. |  |  |  | Project Sponsors and / or Accountable Org. Levels

## Risk Assessment
Risk ID | Risk Item | Impact | Likelihood | Risk Score | Comments | Mitigation
Mitigation |  | Mitigation | Mitigation |  |  | Mitigation
1 | Complexity of System Interfaces - System Interface requiredments becomes complex to handle | 4 | 2 | 4.4721 | Understanding the no of interfaces with other systems and their requirements | Draft the user requirements and meet-up with the customer face-to-face to run through the URS to iorn out any gaps or misunderstandings on the system interface requirements
2 | Technical Complexity - No of technical components that the team ha limited knowledge at this time | 4 | 3 | 5 | Understanding the technical complexity of the project and being able to deliver the project | Project team to conduct and carry out necessary POC during iterration 0 to get familirize with the hardware technology
3 | User Requirements to confirm the scope - Clarity on the scope and next level user requirements | 4 | 2 | 4.4721 | Finalization of User requirements | Draft the user requirements and meet-up with the customer face-to-face to run through the URS to iorn out any gaps or misunderstandings.
4 | Expectatations on the Real time Performance of the system | 3 | 3 | 4.2426 | Expectations on the systems performance(Real time) | Well optimized code to be deployed, have reviews conducted on the code before deployment for testing to see it is well optmized. Keep the stakeholders informed of the limitations driven by the technical architecture
5 | Hardware Technology adapted by the project | 4 | 1 | 4.1231 | Project team's familiarity of the Hardware Technology to be adapted by the proposed system | Project team to conduct and carry out necessary POC during iterration 0 to get familirize with the hardware technology
6 | Finalization of Project Plan | 3 | 3 | 4.2426 | Project Plan with Mile stones and expected deliverables agreed and accepted by relevant stakeholders | Draft the project plan and meet-up with the customer face-to-face to run through the Project plan. This will help to iorn out any gaps or misunderstandings interms milestones and deliverables.
7 | Limited technical skill sets - cloud services - rich UI for real time analytic - LabView | 2 | 1 | 2.2361 |  | 1. Do some POC work to ensure the concepts is workable and doable 2. Consult some experts to get some idea
8 | Withdrawing of team member during the project | 3 | 0 | 3 |  | 1. Make sure every team member is familiar in all major and critical modules.
9 | Remote stations can be disconnected from network for any reason during system integration testing | 1 | 3 | 3.1623 |  | 1. Well plan for integration testing with remote stations. 2. Discuss with remote stations infrastructure team to execute test plans for all scenarios.
10 | Lack of knowledge on project business domain | 2 | 2 | 2.8284 |  | 1. Get detailed documentation from business user understand their business domain. 2. Face-to-Face discussion with business user
11 | Failure or laggy performance of application's end point api because of multiple requests from different remote stations at the same time. | 1 | 4 | 4.1231 |  | 1. In order to meet the performance requirement, it is better that we design the system well during the design stages 2. Try to involve some experts to design the architecture first 3. Ensure the sufficient loading and performance testing along the way 4. In case of encountering the performance issue, we try to tune performance immediately not till the end of the project.
12 | Misunderstanding of the client's requirement and implemented some functionlity wrongly | 3 | 2 | 3.6056 |  | 1. Requirement specification should be documented with all the scenarios and constraints. Before we start, all the changes should be documented and get proper sign off from user.

## Risk Check-Box List
Risk ID | Risk Item | Impact | [5 empty] | Likelihood | [5 empty] | Risk Score | Comments | Mitigation
Mitigation |  | Reduce Functionality 1 | Increased Cost 2 | Schedule Slippage 3 | Quality Cost 4 | Performance 5 | Total | Novelty 1 | Product History 2 | Project Team History 3 | Recognized Authority 4 | Expectation 5 | Total |  |  | Mitigation
1 | Complexity of System Interfaces - System Interface requiredments becomes complex to handle | x | x | x | - | x | 4 | x | - | - | x | x | 2 | 4.4721 | Understanding the no of interfaces with other systems and their requirements
2 | Technical Complexity - No of technical components that the team ha limited knowledge at this time | - | x | x | x | x | 4 | - | x | x | x | - | 3 | 5 | Understanding the technical complexity of the project and being able to deliver the project
3 | User Requirements to confirm the scope - Clarity on the scope and next level user requirements | x |  | x | x | x | 4 | - | - | - | x | x | 2 | 4.4721 | Finalization of User requirements
4 | Expectatations on the Real time Performance of the system | - | x | - | x | x | 3 | - | x | - | x | x | 3 | 4.2426 | Expectations on the systems performance(Real time)
5 | Hardware Technology adapted by the project | - | x | x | x | x | 4 | - | - | - | x | - | 1 | 4.1231 | Project team's familiarity of the Hardware Technology to be adapted by the proposed system
6 | Finalization of Project Plan | - | x | x | x | - | 3 | - | - | x | x | x | 3 | 4.2426 | Project Plan with Mile stones and expected deliverables agreed and accepted by relevant stakeholders
7 | Limited technical skill sets - cloud services - rich UI for real time analytic - LabView | - | - | x | - | x | 2 | x | - | - | - | - | 1 | 2.2361 |  | 1. Do some POC work to ensure the concepts is workable and doable 2. Consult some experts to get some idea
8 | Withdrawing of team member during the project | x |  | x | x |  | 3 | - | - | - | - | - | 0 | 3 |  | 1. Make sure every team member is familiar in all major and critical modules.
9 | Remote stations can be disconnected from network for any reason during system integration testing | - | - | x |  | - | 1 | x | - | - | x | x | 3 | 3.1623 |  | 1. Well plan for integration testing with remote stations. 2. Discuss with remote stations infrastructure team to execute test plans for all scenarios.
10 | Lack of knowledge on project business domain | - | - | x | x | - | 2 | - | - | x |  | x | 2 | 2.8284 |  | 1. Get detailed documentation from business user understand their business domain. 2. Face-to-Face discussion with business user
11 | Failure or laggy performance of application's end point api because of multiple requests from different remote stations at the same time. | - | - | - | - | x | 1 | x | x | - | x | x | 4 | 4.1231 |  | 1. In order to meet the performance requirement, it is better that we design the system well during the design stages 2. Try to involve some experts to design the architecture first 3. Ensure the sufficient loading and performance testing along the way 4. In case of encountering the performance issue, we try to tune performance immediately not till the end of the project.
12 | Misunderstanding of the client's requirement and implemented some functionlity wrongly | x |  | x |  | x | 3 | x | - | x | - | - | 2 | 3.6056 |  | 1. Requirement specification should be documented with all the scenarios and constraints. Before we start, all the changes should be documented and get proper sign off from user.