## WBS
Activity | Task | Agnes | Bala | KM | NL | Tresa | William
1 | Project Planing
Project Kickoff meeting
Define project scope
Review project scope
Setup project filing system
Project risk tracker
Prepare WBS
Use case point estimating
Produce project plan document
Review/Finalize project plan document
Produce quality plan
Review/Finalize quality plan
2 | Requirement Identification
Project requirement gathering
Produce User requirement specification
Review/Finalize User requirement specification
Produce Use Case Modelling survey report
Review/Finalize Use Case Modelling survey report
Produce User Interface Speficication
Review/Finalize User Interface Specification
3 | Requirement Analysis
Produce Prototype Study Report
Review/Finalize Prototype Study Report
Produce High Level Design Specification
Review/Finalize High Level Design Specification
4 | Incorporate Audit Feedbacks
Ad-hoc Management
Revised on Audit Comments
Prepare for presentation
5 | Analysis and Design Modelling (Increment 1)
Identify Domain Objects/Attributes
Produce Class Diagram/Collaboration Diagram
Produce Use Case Model Survey Report (Requirement)
Review/FinaliseUse Case Model Survey Report (Requirement)
Produce Use Case Model Survey Report (Analysis)
Review/FinaliseUse Case Model Survey Report (Analysis)
Define Object Associations
Produce Design Model Report
Review/FinaliseDesign Model Report
6 | Implementation & Coding
Setup necessary cloud environment
Source control plan and setup
Coding
Unit testing
Peer review coding
7 | Testing
Produce System Test Plan
Review/Finalise System Test Plan
Perform System Testing
Bug Review/Corrective action/Rework
Prepare SIT Document
Review/Finalise SIT Document
Prepare User Acceptance Test Plan
Review/Finalise Acceptance Test Plan
Perform Integration Testing with PT07
Review Test Result and perform Corrective Action
End User Training Manual and Write User Guide
Review/Finalise User Guide
Perform User Acceptance Testing
Review Acceptance Test Result/Corrective Action
Prepare User Acceptance Test Document
Review/Finalise User Acceptance Test Document
8 | Revised Documentation for 2nd Audit
Revised High Level Design Specification
Revised Project Plan
9 | Incorporate Audit Feedbacks
Ad-hoc Management
Revised on Audit Comment
Prepare for Presentation
10 | Analysis and Design Modelling (Increment 2)
Identify Domain Objects/Attributes
Produce Class Diagram/Collaboration Diagram
Produce Use Case Model Survey Report (Requirement)
Review/FinaliseUse Case Model Survey Report (Requirement)
Produce Use Case Model Survey Report (Analysis)
Review/FinaliseUse Case Model Survey Report (Analysis)
Define Object Associations
Produce Design Model Report
Review/FinaliseDesign Model Report
11 | Programming (Increment 2)
Coding
Unit Testing
Peer Review of Coding
12 | Testing (Increment 2)
Produce System Test Plan
Review/Finalise System Test Plan
Perform System Testing
Bug Review/Corrective action/Rework
Prepare SIT Document
Review/Finalise SIT Document
Prepare User Acceptance Test Plan
Review/Finalise Acceptance Test Plan
Perform Integration Testing with PT07
Review Test Result and perform Corrective Action
Performance Testing
End User Training Manual and Write User Guide
Review/Finalise User Guide
Perform User Acceptance Testing
Review Acceptance Test Result/Corrective Action
Prepare User Acceptance Test Document
Review/Finalise User Acceptance Test Document
13 | Implementation
Source Deployment Process Guide
AWS setup and manual
Release Project
Prepare User Training
Training User
Revised Documents and Sign-Off
Project Hand-over
14 | Incorporate Audit Feedbacks
Ad-hoc Management
Revised on Audit Comment
Prepare for Presentation