## WBS
Activity | Task | Agnes | Bala | KM | NL | Tresa | William
1 | Project Planing
Project Kickoff meeting
Define project scope
Review project scope
Setup project filing system
Project risk tracker
Prepare WBS
Use case point estimating
Produce project plan document
Review/Finalize project plan document
Produce quality plan
Review/Finalize quality plan
2 | Requirement Identification
Project requirement gathering
Produce User requirement specification
Review/Finalize User requirement specification
Produce Use Case Modelling survey report
Review/Finalize Use Case Modelling survey report
Produce User Interface Speficication
Review/Finalize User Interface Specification
3 | Requirement Analysis
Produce Prototype Study Report
Review/Finalize Prototype Study Report
Produce High Level Design Specification
Review/Finalize High Level Design Specification
4 | Incorporate Audit Feedbacks
Ad-hoc Management
Revised on Audit Comments
Prepare for presentation
5 | Analysis and Design Modelling (Increment 1)
Identify Domain Objects/Attributes
Produce Class Diagram/Collaboration Diagram
Produce Use Case Model Survey Report (Requirement)
Review/FinaliseUse Case Model Survey Report (Requirement)
Produce Use Case Model Survey Report (Analysis)
Review/FinaliseUse Case Model Survey Report (Analysis)
Define Object Associations
Produce Design Model Report
Review/FinaliseDesign Model Report
6 | Implementation & Coding
Setup necessary cloud environment
Source control plan and setup
Coding
Unit testing
Peer review coding
7 | Testing
Produce System Test Plan
Review/Finalise System Test Plan
Perform System Testing
Bug Review/Corrective action/Rework
Prepare SIT Document
Review/Finalise SIT Document
Prepare User Acceptance Test Plan
Review/Finalise Acceptance Test Plan
Perform Integration Testing with PT07
Review Test Result and perform Corrective Action
End User Training Manual and Write User Guide
Review/Finalise User Guide
Perform User Acceptance Testing
Review Acceptance Test Result/Corrective Action
Prepare User Acceptance Test Document
Review/Finalise User Acceptance Test Document
8 | Revised Documentation for 2nd Audit
Revised High Level Design Specification
Revised Project Plan
9 | Incorporate Audit Feedbacks
Ad-hoc Management
Revised on Audit Comment
Prepare for Presentation
10 | Analysis and Design Modelling (Increment 2)
Identify Domain Objects/Attributes
Produce Class Diagram/Collaboration Diagram
Produce Use Case Model Survey Report (Requirement)
Review/FinaliseUse Case Model Survey Report (Requirement)
Produce Use Case Model Survey Report (Analysis)
Review/FinaliseUse Case Model Survey Report (Analysis)
Define Object Associations
Produce Design Model Report
Review/FinaliseDesign Model Report
11 | Programming (Increment 2)
Coding
Unit Testing
Peer Review of Coding
12 | Testing (Increment 2)
Produce System Test Plan
Review/Finalise System Test Plan
Perform System Testing
Bug Review/Corrective action/Rework
Prepare SIT Document
Review/Finalise SIT Document
Prepare User Acceptance Test Plan
Review/Finalise Acceptance Test Plan
Perform Integration Testing with PT07
Review Test Result and perform Corrective Action
Performance Testing
End User Training Manual and Write User Guide
Review/Finalise User Guide
Perform User Acceptance Testing
Review Acceptance Test Result/Corrective Action
Prepare User Acceptance Test Document
Review/Finalise User Acceptance Test Document
13 | Implementation
Source Deployment Process Guide
AWS setup and manual
Release Project
Prepare User Training
Training User
Revised Documents and Sign-Off
Project Hand-over
14 | Incorporate Audit Feedbacks
Ad-hoc Management
Revised on Audit Comment
Prepare for Presentation

## Milestones
Project Milestones |  | Approx. Date
Increment 0
1.1 | Issue Work Breakdown Structure | 2018-03-06
1.2 | Issue Use Case Modelling Survey Report | 2018-03-28
1.3 | Issue Prototype Study Report | 2018-04-15
1.4 | Issue Risk Tracker | 2018-03-15
1.5 | Issue Project Plan Doc | 2018-04-12
1.6 | Issue User Requirement Specification Doc | 2018-04-15
1.7 | Issue User Interface Specification Doc | 2018-04-17
1.8 | Issue High Level Design Doc | 2018-04-14
1.9 | Issue Quality Plan Doc | 2018-04-14
1.10 | Implement Prototype | 2018-04-15
Increment 1
2.1 | Setup Cloud Environment | 2018-05-02
2.2 | Issue Use Case Modelling Survey Report(Analysis) | 2018-05-06
2.3 | Issue Design Report | 2018-05-20
2.4 | Complete Source Control Plan and Setup | 2018-05-01
2.5 | Complete Coding | 2018-07-15
2.6 | Issue System Test Plan | 2018-05-20
2.7 | Complete System Testing | 2018-07-22
2.8 | Complete Integration Test | 2018-07-29
2.9 | Issue SIT Document | 2018-08-05
2.10 | Issue User Acceptance Test Plan | 2018-08-05
2.11 | Issue End User Traning Manual and User Guide | 2018-08-12
2.12 | Complete User Acceptance Testing | 2018-08-19
2.13 | Issue User Acceptance Test Document | 2018-07-25
Increment 2
3.1 | Setup Cloud Environment | 2018-09-02
3.2 | Issue Use Case Modelling Survey Report(Analysis) | 2018-09-09
3.3 | Issue Design Report | 2018-09-16
3.4 | Complete Source Control Plan and Setup | 2018-09-02
3.5 | Complete Coding | 2018-11-18
3.6 | Issue System Test Plan | 2018-11-23
3.7 | Complete System Testing | 2018-11-25
3.8 | Complete Integration Test | 2018-12-02
3.9 | Issue SIT Document | 2018-12-09
3.10 | Issue User Acceptance Test Plan | 2018-12-09
3.11 | Issue End User Traning Manual and User Guide | 2018-12-16
3.12 | Complete User Acceptance Testing | 2018-12-09
3.13 | Issue User Acceptance Test Document | 2018-12-16
3.14 | Complete AWS setup and manual | 2018-12-23
3.15 | Commence User Traning | 2018-12-23
3.16 | Project Hand-over | 2018-12-31