## Status Tracking
% Complete | Task Name | Duration | Start | Finish | Work | Earned Value | Remaning
100% | Project Initiation | 52 days | Thu 01-02-18 | Fri 13-04-18 | 428 hrs | 428 | 0
100% | Build Prototype | 9 days | Mon 16-04-18 | Thu 26-04-18 | 50 hrs | 50 | 0
100% | Incorporate Audit Feedbacks | 4 days | Fri 27-04-18 | Wed 02-05-18 | 40 hrs | 40 | 0
100% | Analysis and Design Modelling (Increment 1) | 32 days | Thu 03-05-18 | Fri 15-06-18 | 294 hrs | 294 | 0
100% | Implementation & Coding | 52 days | Thu 10-05-18 | Fri 20-07-18 | 226 hrs | 226 | 0
67% | Testing | 51 days | Mon 18-06-18 | Mon 27-08-18 | 306 hrs | 205.02 | 100.98
100% | Revised Documentation for 2nd Audit | 1 day | Tue 28-08-18 | Tue 28-08-18 | 4 hrs | 4 | 0
100% | Incorporate Audit Feedbacks | 4 days | Tue 28-08-18 | Fri 31-08-18 | 32 hrs | 32 | 0
100% | Analysis and Design Modelling (Increment 2) | 32 days | Mon 03-09-18 | Tue 16-10-18 | 294 hrs | 294 | 0
90% | Programming (Increment 2) | 30 days | Wed 17-10-18 | Tue 27-11-18 | 240 hrs | 216 | 24
61% | Testing (Increment 2) | 55 days | Wed 17-10-18 | Tue 01-01-19 | 306 hrs | 186.66 | 119.34
19% | Implementation | 41 days | Wed 21-11-18 | Wed 16-01-19 | 106 hrs | 20.14 | 85.86
0% | Incorporate Audit Feedbacks | 4 days | Thu 17-01-19 | Tue 22-01-19 | 32 hrs | 0 | 32
[5 empty] | Hours | 1995.82 | 362.18
[5 empty] | Percentage | 84.64% | 15.36%